## Tasks
Minimum List of Group Project Task |  | EEET2580 Teamwork Contribution Document
You should add more based on your group's work |  | SQUAD ACE - GROUP B
Design ERD |  | Name: Trung Le Tran Minh |  |  | Name: Pavel Potemkin |  |  | Name: Saurabh Padmakumar |  |  | Name: Nguyen Do Khoa |  |  | Name: Kien Vo Nguyen
Refine ERD |  | Assigned Tasks | Target Date | Date Completed | Assigned Tasks | Target Date | Date Completed | Assigned Tasks | Target Date | Date Completed | Assigned Tasks | Target Date | Date Completed | Assigned Tasks | Target Date | Date Completed
MILESTONE 1
Review ERD | ERD Design | Design ERD | 20/11/2024 | 20/11/2024 | Review ERD | 25/11/2024 | 25/11/2024 | Review ERD | 25/11/2024 | 25/11/2024 | Design ERD | 20/11/2024 | 20/11/2024 | Review ERD | 25/11/2024 | 25/11/2024
|  | Refine ERD | 25/11/2024 | 25/11/2024 | [6 empty] | Refine ERD
Design System Architecture for Level X Requirement RXY
Refine System Architecture for Level X Requirement RXY | Architecture Design | Design System Architecture for Level 1 Requirement 2B.2.1 | 23/11/2024 | 23/11/2024 | Design System Architecture for Level 1 Requirement 2B.2.2 | 23/11/2024 | 23/11/2024 | Design System Architecture for Level 1 Requirement 2B.2.5 | 23/11/2024 | 23/11/2024 | Design System Architecture for Level 1 Requirement 2B.1.1 | 23/11/2024 | 23/11/2024 | Design System Architecture for Level 1 Requirement 2B.2.3 | 23/11/2024 | 23/11/2024
Review System Architecture for Level X Requirement RXY |  | Design System Architecture for Level 2 Requirement 2B.2.1 | 23/11/2024 | 23/11/2024 | Design System Architecture for Level 1 Requirement 2B.2.3 | 23/11/2024 | 23/11/2024 | Design System Architecture for Level 2 Requirement 2B.2.6 | 23/11/2024 | 23/11/2024 | Design System Architecture for Level 1 Requirement 2B.1.2 | 23/11/2024 | 23/11/2024 | Design System Architecture for Level 2 Requirement 2B.2.7 | 23/11/2024 | 23/11/2024
|  | Design System Architecture for Level 2 Requirement 2B.2.2 | 23/11/2024 | 23/11/2024 | Design System Architecture for Level 1 Requirement 2B.2.4 | 23/11/2024 | 23/11/2024 | Design System Architecture for Level 2 Requirement 2B.2.7 | 23/11/2024 | 23/11/2024 | Design System Architecture for Level 2 Requirement 2B.1.1 | 23/11/2024 | 23/11/2024 | Design System Architecture for Level 2 Requirement 2B.2.1 | 23/11/2024 | 23/11/2024
Design UX/UI for Level X Requirement RXY |  | Design System Architecture for Level 2 Requirement 2B.2.5 | 23/11/2024 | 23/11/2024 | Design System Architecture for Level 2 Requirement 2B.2.3 | 23/11/2024 | 23/11/2024 | Design System Architecture for Level 3 Requirement 3B.2.1 | 28/11/2024 | 28/11/2024 | Design System Architecture for Level 2 Requirement 2B.1.2 | 23/11/2024 | 23/11/2024 | Design System Architecture for Level 2 Requirement 2B.2.2 | 23/11/2024 | 23/11/2024
Refine UX/UI for Level X Requirement RXY |  | Design System Architecture for Level 3 Requirement 3B.1.1 | 28/11/2024 | 28/11/2024 | Design System Architecture for Level 2 Requirement 2B.2.4 | 23/11/2024 | 23/11/2024 | Design System Architecture for Level 3 Requirement 3B.3.1 | 28/11/2024 | 28/11/2024 | Design System Architecture for Level 3 Requirement 3B.1.1 | 28/11/2024 | 28/11/2024 | Design System Architecture for Level 3 Requirement 3B.2.1 | 28/11/2024 | 28/11/2024
Review UX/UI for Level X Requirement RXY |  | Design System Architecture for Level 3 Requirement 3B.1.2 | 28/11/2024 | 28/11/2024 | Design System Architecture for Level 3 Requirement 3B.2.1 | 28/11/2024 | 28/11/2024 | Refine System Architecture for Level 2 Requirement 2B.2.3 | 25/11/2024 | 25/11/2024 | Design System Architecture for Level 3 Requirement 3B.1.2 | 28/11/2024 | 28/11/2024 | Refine System Architecture for Level 3 Requirement 3B.3.1 | 25/11/2024 | 25/11/2024
|  | Refine System Architecture for Level 1 Requirement 2B.2.3 | 25/11/2024 | 25/11/2024 | Refine System Architecture for Level 2 Requirement 2B.2.6 | 25/11/2024 | 25/11/2024 | Refine System Architecture for Level 1 Requirement 2B.2.3 | 25/11/2024 | 25/11/2024 | Refine System Architecture for Level 2 Requirement 2B.2.2 | 25/11/2024 | 25/11/2024 | Refine System Architecture for Level 1 Requirement 2B.2.3 | 25/11/2024 | 25/11/2024
|  | Document profile management component [Diagram] | 30/11/2024 | 30/11/2024 | Document project management component [Diagram/Justification] | 2024-01-12 | 2024-01-12 | Document statistics component [Diagram/Justification] | 2024-01-12 | 2024-01-12 | Document API gateway [Diagram/Justification] | 2024-01-12 | 2024-01-12 | Document profile management component [Diagram/Justification] | 2024-01-12 | 2024-01-12
HTML/CSS for Level X Requirement RXY |  | Document table component [Diagram/Justification] | 2024-01-12 | 2024-01-12 | Document state management solutions [Diagram/Justification] | 2024-01-12 | 2024-01-12 | Document table component [Diagram] | 30/11/2024 | 30/11/2024 | Document system authentication components [Diagram/Justification] | 2024-01-12 | 2024-01-12 | Document table component [Justification] | 2024-02-11 | 2024-02-11
|  | Document back-end and front-end containers [Diagram] | 30/11/2024 | 30/11/2024 | Document table component [Diagram] | 30/11/2024 | 30/11/2024 | Document form component [Diagram/Justification] | 2024-01-12 | 2024-01-12 | Document table component [Diagram] | 30/11/2024 | 30/11/2024 | Document chart component [Justification] | 2024-02-11 | 2024-02-11
|  | Document resilience, security, performance of back end architecture [Justification] | 2024-02-11 | 2024-02-11 | Document modal form component [Diagram] | 30/11/2024 | 30/11/2024 | Document back-end and front-end containers [Diagram] | 30/11/2024 | 30/11/2024 | Document back-end and front-end containers [Diagram] | 30/11/2024 | 30/11/2024 | Document back-end and front-end containers [Diagram] | 30/11/2024 | 30/11/2024
|  | Document front-end containers [Justification] | 30/11/2024 | 30/11/2024 | Document back-end and front-end containers [Diagram] | 30/11/2024 | 30/11/2024 | Document overall architectural choices [Justification] | 2024-02-11 | 2024-02-11 | Document back-end containers [Justification] | 2024-02-11 | 2024-02-11 | Document data transfer object and interfaces [Justification] | 2024-02-11 | 2024-02-11
|  | Document ERD + its advantages and drawback | 26/11/2024 | 26/11/2024 | Document chart component [Diagram] | 2024-02-11 | 2024-02-11 | Document chart component [Diagram] | 30/11/2024 | 30/11/2024 | Document front-end API client component [Diagram/Justification] | 2024-01-12 | 2024-01-12
MILESTONE 2
SQL Queries for Level X Requirement RXY | UX / UI Design
Back-end Implementation for Level X Requirement RXY
Document [R0X] [Diagram/Justification]
Refine [R0X] [Diagram/Justification]
Review [R0X] [Diagram/Justification] | Front-end Development
Task of your own choice
Back-end Development
Reporting